This is a fictional example. The studio, clients, people and dates are made up to show how this might be filled in. It continues the scope of work, status report and meeting notes examples.

WIP meeting agenda

30 minutes, once a week. Every live project, in the same order.

| Date and time: Monday 2 November 2026, 9:00–9:30 am | Where: At the studio, Jordan on video |
| --- | --- |
| Chair: Chris Example |  |
| Who's there: Chris Example, Alex Example, Jordan Example, Pat Example (Example Design Studio, fictional) |  |

Chair: the person who keeps time and reads back the actions at the end.

Last week's actions Before the meeting

The chair fills this in before the meeting starts: done or not done, nothing more. Anything not done goes into item 1 or 2.

| What | Who | By when | Done? |
| --- | --- | --- | --- |
| First drafts of the window poster and Instagram posts to Jane | Chris | Mon 26 Oct | Yes |
| Chase Jane for the menu wording (due Fri 23 Oct) | Chris | Mon 26 Oct | Yes, arrived Tue 27 Oct |
| Logo version 2 to Jane | Alex | Wed 28 Oct | Yes |
| Booking page test version to Lee | Jordan | Fri 30 Oct | No. See item 1 |

1. Late or at risk 10 min

Start here, not with the biggest client. For each one: what's wrong, what moves if it stays late, and one decision before you move on. Fix it after the meeting, not in it.

| Project | What's wrong | What moves if it's late | Decision |
| --- | --- | --- | --- |
| Citizen Physio website update | Booking page test version was due Fri 30 Oct and hasn't gone. Jordan is also doing the services pages. | Go-live has already moved from Thursday 5 November to Thursday 12 November. If the test version misses Wednesday 4 November, go-live and the clinic's email to patients move again. | Go-live moves to Thu 12 Nov. Pat takes the services pages. Jordan finishes the booking page: test version to Lee by Wed 4 Nov. Chris tells Lee today. |

2. Due this week 8 min

Read out every date between today and Friday. The owner answers yes or no: still on track? A no goes straight into the actions.

| Day | What's due | Project | Who | On track? |
| --- | --- | --- | --- | --- |
| Tue 3 Nov | Instagram posts version 2 to Jane | Café | Alex | Yes |
| Tue 3 Nov | Written quote and new dates: coffee cup stamp | Café | Chris | Yes |
| Wed 4 Nov | Booking page test version to Lee | Physio | Jordan | See item 1 |
| Thu 5 Nov | 10:00 am phone call with Jane: final menu and poster | Café | Chris | Yes |
| Fri 6 Nov | Jane's final OK, all items | Café | Jane | If feedback arrives today |

3. Waiting on the client 5 min

For each client: one person sends one email, with every ask in it, by a set time today. Write who and when here. Use the email template.

| Client | What we need, and by when | Who sends it | Sent by |
| --- | --- | --- | --- |
| Jane Citizen (café) | Feedback on the menu and poster drafts, and the OK on logo version 2: today. Three photos of the new counter: Wed 4 Nov. | Chris | 11:00 am today |
| Morgan Citizen (bakery) | The new catering prices: Mon 16 Nov. If not, we restart the brochure in the new year. | Pat | 5:00 pm today |

4. New work and who has room 5 min

New jobs, quotes and change requests. Before the meeting, each person writes the days they have free this week next to their name. Nobody takes new work beyond that.

| New work | Who has room | Next step |
| --- | --- | --- |
| Services pages (physio), moved from Jordan | Pat (bakery brochure on hold) | Starts today |
| Coffee cup stamp (café), only if Jane says yes to the quote | Alex, from Mon 9 Nov | Chris sends the quote by Tue 3 Nov |

5. Read back the actions 2 min

The chair reads every action out: what, who, by when. An action without a name or a date isn't an action yet. Send the list to everyone straight after.

☒ Actions read back and sent to everyone

Actions

One line per action. Start each one with a verb.

| What | Who | By when |
| --- | --- | --- |
| Send one email to Jane: feedback and logo OK today, counter photos by Wed 4 Nov | Chris | Mon 2 Nov, 11:00 am |
| Tell Lee go-live moves to Thu 12 Nov | Chris | Mon 2 Nov |
| Send one email to Morgan: new prices by Mon 16 Nov, or we restart in the new year | Pat | Mon 2 Nov, 5:00 pm |
| Hand the services pages over to Pat | Jordan | Mon 2 Nov |
| Send Instagram posts version 2 to Jane | Alex | Tue 3 Nov |
| Send the written quote and new dates: coffee cup stamp | Chris | Tue 3 Nov |
| Send the booking page test version to Lee | Jordan | Wed 4 Nov |

Next WIP meeting: Monday 9 November 2026, 9:00 am