## WIP list
WIP list
One row per live project. Update it before the weekly WIP meeting. Stage, Waiting on and Risk are drop-down lists. Fill in Hours used by hand from your own records. On Hold jobs get no Risk label. Add won or likely jobs with Stage left blank and the start date as Next deadline.
Project | Client | Stage | Next deadline | Waiting on | Owner | Risk | What moves if it's late | Hours used (write in by hand) | Next step

## Example (fictional)
This is a fictional example. The studio, clients, people and dates are made up to show how this might be filled in. It matches the WIP meeting agenda example for Monday 2 November 2026.
WIP list — Monday 2 November 2026
One row per live project. Update it before the weekly WIP meeting. Stage, Waiting on and Risk are drop-down lists. Fill in Hours used by hand from your own records. On Hold jobs get no Risk label. Add won or likely jobs with Stage left blank and the start date as Next deadline.
Project | Client | Stage | Next deadline | Waiting on | Owner | Risk | What moves if it's late | Hours used (write in by hand) | Next step
Example Street Café reopening | Example Street Café (Jane Citizen) | In Progress | 2026-11-06 | Client | Chris Example | At risk | Files to the printer move from Monday 9 November, and the reopening on Saturday 21 November is at risk. |  | Final OK, all items, Fri 6 Nov. Chris emails Jane by 11:00 am today: feedback today, counter photos by Wed 4 Nov.
Citizen Physio website update | Citizen Physio (Lee Citizen) | In Progress | 2026-11-04 | Us | Jordan Example | Late | Go-live has already moved from Thursday 5 November to Thursday 12 November. If the test version misses Wednesday 4 November, go-live and the clinic's email to patients move again. |  | Booking page test version to Lee by Wed 4 Nov. Go-live now Thu 12 Nov. Pat takes the services pages.
Citizen Bakery catering brochure | Citizen Bakery (Morgan Citizen) | On Hold | 2026-11-16 | Client | Pat Example |  | The printed brochures miss the start of Christmas catering orders on Tuesday 1 December. |  | New catering prices due Mon 16 Nov. Pat emails Morgan by 5:00 pm today.